## Form NTL
OMB form 0412-0562 AID-1570-13 (exp: 06/30/2011)
NARRATIVE/TIME-LINE REPORT (NTL) Quarterly Progress Report on a Major Program Activity
1. NARRATIVE - Accomplishments this reporting period
2. TIMELINE and PROGRESS SCHEDULE
NOTE! - Express all dates in month/year - Show event numbers (no more than 8) along each time-line
Planned time-line | year:
Actual time-line
QPR No.
event-completion during the month of: | [6 empty] | planned | actual | event - completion during the month of: |  | planned | actual
1. | [6 empty] | - | - | 5. |  | - | -
2. | [6 empty] | - | - | 6. |  | - | -
3. | [6 empty] | - | - | 7. |  | - | -
4. | [6 empty] | - | - | 8. |  | - | -
3. PROBLEMS CAUSING DELAYED EVENTS | [8 empty] | 4. PROPOSED SOLUTIONS
USO (Grantee) |  |  | name, city, state
OSI (Overseas Inst.) |  |  | name, city, country
QPR No. |  |  | Activity No. |  |  | Description:
period covered: | 1st | 2nd | 3rd | 4th | calendar quarter of |  |  | HSH-G-00-__-____ (ASHA ____-___) |  | date:

## NTL Instructions
INSTRUCTIONS FOR NARRATIVE/TIMELINE (NTL) REPORT
Quarterly Progress Report on a Major Program Activity
PREAMBLE
Create a narrative/timeline master set by completing one of these forms for each major program activity. In block 2, show each event,
the planned completion date, and its identification number along the planned time-line. Once the master form is created, you may
reproduce it quarterly before filing your progress report, which will consistently show the originally planned timeline. When comparing
the planned and the actual completion dates (deadlines), any delay will signify a problem. The report will describe the problems and
proposed solutions in blocks 3 and 4 respectively. One solution could be the revision of an ill-conceived timeline and the creation of a
new master form.
DEFINITIONS
According to Attachment 3, Art.7.1 of the agreement, the grantee shall submit a narrative timeline quarterly report. Program activities
may be funded by any of the budget line items authorized by the grant. The quarterly progress report is due for each major
activity, whether or not progress is being made. A major activity is any sub-program goal, such as the construction of a building,
major or minor renovation of a building or department, or achieving a programmatic goal in training or research.
SUBSTANCE
To ease and standardize reporting for each major program activity and to assure compliance by grantees, USAID-ASHA requests
that each award recipient use a form identical to that represented on the other side of this page. The grantee should add any
other report or photograph received from its sponsored Overseas institution (OSI). In general, the grantee will provide the following
information on a quarterly basis:
Block 1. - Accomplishments
A brief narrative description of primary tasks completed, during the reporting period, with the intent to bring the major activity's
goal and purpose to fruition.
|  | i. | For construction, tasks may be any of, but not limited to, the following: - design - advertise for bid - contract award -
mobilization - excavation - concreting for footing, for columns, for slabs, for walls - erecting framework - masonry walls -
partitions - roofing - landscaping – etc…
|  | ii. | For renovation, tasks may be any of, but not limited to, the following: - planning - contracting - demolition of non
bearing structures - rearrangement of interior partitions or openings - upgrading utilities - patching - painting - finishing -
landscaping – etc…
|  | iii. | For acquisition of goods and materials (including rolling stock), tasks may be any of, but not limited to, the following:
writing specifications - advertising - selecting suppliers - shipping - installing - training - inventorying – etc…
|  | iv. | For program support, tasks may be, but not limited to, planning of sub-activities - contracting with consultants -
awarding scholarship - opening ceremonies - etc…
Block 2 - Timeline and Progress Schedule
At the start of a major activity (within 90 days after the grant award), the grantee will have had a planned schedule that will lead
to its realization by the project assistance completion date (PACD). The planned schedule will contain a number of critical deadlines
(not to exceed eight) that will serve to monitor whether or not the program is on target. Express each event with a very short
sentence (two to four words) and show, in each report, their respective numbers along the “planned” and the “actual” timelines.
|  | i. | For construction, events may be any of, but not limited to, the completion of the following: signing of AE contract - preliminary -
bid package - contract award - foundations - roof structure - finishing - dedication - etc…
|  | ii. | For renovation, events may be any of, but not limited to, the completion of the following: - technical report - contract awards -
refurbishing area A - refurbishing Area B - occupy premises - etc…
|  | iii. | For acquisition of goods and materials (including rolling stock), events may be any of, but not limited to, the following:
complete specifications - complete advertising - complete selecting suppliers - complete shipping - complete installation in
Area A - complete installation in Area B – complete end-users' training - sign final inventory - etc…
|  | iv. | For program support, events may be any of, but not limited to, the completion of the following: planning - expressions
of interest - contracting consultants - evaluating results - etc…
Block 3 - Problems Causing Delayed Events and Block 4 - Proposed Solutions
No major activity, whether it be construction, renovation, procurement of commodities, or other program targets, is immune
from occasional problems. Factors affecting the attainment of the proposed time schedule for completing a major activity may
be: inclement weather - civil unrest - lack of materials - bad contractors' performance - bureaucratic hurdles - lack of qualified
personnel – etc… Problems should not be left unattended, however. Both the grantee and the OSI must work together to
identify means to mitigate the ill effects that any problem may impose upon the attainment of a major activity. The grantee will
report in their assigned areas any and all such concerns and proposed solutions that would bring the activity back on track.
(back of NTL)

## NTL Instructions 2
Public reporting burden for this collection of information is estimated to average 3 hours per response, including the time for
reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and
reviewing the collection of information. The Agency may not conduct or sponsor, and a person is not required to respond to, a
collection of information unless it displays a currently valid OMB control number. Send comments regarding this burden
estimate or any other aspect of this collection of information, including suggestions for reducing this burden, to American Schools
and Hospitals Abroad, US Agency for International Development, Ronald Reagan Building, 1300 Pennsylvania Ave. NW,
Washington, DC 20523-3800.